## 请求资料
| 工时（天） | 金额 | 实际请求金额（元）
原合同范围内障害对应 | 11.4 | 11400
合计 | 11.4 | 11400 | 0
较小改善，已完成 | 12.6 | 12600
较大机能改善，已完成 | 23.3 | 23300
合计 | 35.9 | 35900 | 20000
Office版本批量打印对应 | 15 | 15000
合计 | 15 | 15000 | 5000
|  | 合计请求 | 25000

## 详细列表
番号 | 期望 | 类别 | 花费 | 对应 | 对应 情况 | 备注
1 | 1. open files: when go to that option it should direct you straight to WELD DATA folder | 小改善 | 0 |  | cancel | 保持现有
2 | 2. at chart view:-- need to restore cursor grid lines (if hold right button on mouse) | 大改善 | 2 | II | done | 需完善
3 | 3. option with DATA FILTER should be restored for chart view ，（就是过滤数据功能） | 大改善 | 3 | II | done | 只过滤电流 1/4 细节逻辑需对应
4 | 4. All description should be ENGLISH. Its still mane at confirmation buttons at Chinese, also some strange characters pop up during loading/on-line bars running. （进度条出现…） | Bug | 0.2 | I | done | OK
5 | 5. at the end of the weld cycle it shows INTERRUPT instead ok (can only guess what it will show on interrupt weld) (结果判断出错) | Bug | 0.3 | I | done | 判断逻辑需要确认
6 | 6. Screen: font suggest to be change to IMPACT (or similar), patter color to deep-deep blue (next to black) – not a bright one. 希望监控画面使用“IMPACT”字体 | 小改善 | 0.1 | I | done
7 | 7. Date better to have in format like 24 MAR2011, not just digits as it could be confused 。数据格式，包括文件名，日期“24 MAR2011” | 小改善 | 0 |  | cancel | 需探讨
8 | 8. Discussed and agreed dial gauges did not appear and as a get from explanation he is not good enough to make it. Bill—you promise to make it, so please give a time when it will be happened. For now let’s make ALL BARS AT THE BOTTOM OF SCREEN (HORIZONTAL) WITH ALL DESCRIPTIONS LOCATED AT TOP PART (DATE, TIME, READY, WELD NUMBER AND NAME OF PARAMETERS) | 大改善 | 0.3 | I | done | 仪表盘放弃 显示界面已作相应调整
9 | 9. On working screen is permanent horizontal line across the screen—need to get rid of it. 背景颜色为深蓝色。 | 小改善 | 0.1 | I | done
10 | 10. At welding analyses— its shows slippage at every weld. Need to look into it and get it right—NOT JUST disconnect as I did “slippage”判断出错 | bug | 0.5 | I | done | 使用原始“或”逻辑
11 | 11. option of START RECORDING FROM “START” BUTTON—doesn’t work and presents for “beautiful” only 。 |  | 0 |  | cancel | 没有这个问题
12 | 12. suggest to add option (protected by password) of welding parameter set delete (one by one) as at some units it over 30 already and in use only 2 or 3 。建议增加是否用密码保护参数选项。 | 小改善 | 0 |  | cancel | 保留原功能
13 | 14. installation package should be more reliable : with auto set icons on desktop, locate files and folders correct (no need to move it manually after installation etc) | 较大改善 | 0 |  | cancel
14 | 1. Welding Parameters name not reflect in report correctly. （有时出现参数名称显示不正常） | Bug | 0.5 | I | done | SettingName 需要再确认更改是否引起其他问题
15 | 2. Batch print option missed. Print section missed printing option of chart report/multiple chart/chart/report choice. No drop menu with printer choice etc. | 大改善 | 2 | III | done | 追加打印每日报表 其他暂不对应
16 | 3. Office program not good at all- even no any point to start testing. Can’ open old files, mess with printing, mess with chart view options, plenty useless options from plant WMS program, incorrect display data on charts etc etc. | 小改善 | 3 | III | done | 正式版本完全完成后 做成只读版本 其他要求暂时不对应
17 | 4. WMS should not depends of operational system language and can install at any (English, Turkish, French, Thai, Arabic etc) | 大改善 | 4 | III | done | 英文版安装软件，需要找到英文VB6
18 | 5. Impedance reading/calculations at report is incorrect | 小改善 | 0.5 | II | done | 公式由卢工提供 Andrei后续提供建议 >依赖公式提供时间 希望 2011-4-24之前完成
19 | 6. WINDOW drop menu should be renamed (say chart select) as it confusing with operational system | 小改善 | 0.2 | I | done
20 | 7. When PLC controller get power off—its still shows READY not “controller communication failure”. Also WMS get suspended. | 大改善 | 2 | II | done | 需要做 连接出错的时候，报错
21 | 8. If download parameters or get online is failed—still running GREED bar, not red. Did not show message DOWNLOAD SUCCESSFULLY COMPLETED OR FAILED | 大改善 | 8 | II | done | 需要做
22 | At daily report page—can’t highlight weld (line) - which make not easy to work with. Same at data string – cant highlight line | 小改善 | 0.4 | I | done | ？？？？
23 | 9. Could be useful to add option of long (full) number by tick box. Say to add 5 characters in front of Co unit code number (for example like FBW01) and 2 characters at back as operator’s code. So full number will like FBW01A0001VC, that’s will actually match a lot of Companies needs. We will need to add some boxes under weld recording menu, with typing co code and operators code, plus optional tick box between long/short numbers | 大改善 | 2 | II | done | 按FBW01A0001VC 修改编号格式 文件名不需要变更 文件名(A0001) 预定 2011-4-24之前完成
24 | 10. New WMStudio very unreliable on upset and forging reading. Sometimes for upset stage it comes 2-3 spots on chart only. | Bug | 1 | I | done | 记录的数据比较少
25 | 参数在范围外的时候，用红色提醒，但是仍然可以继续使用 | 小改善 | 0.3 | I | done | 参数范围值随后andrei提供
26 | 参数名列表允许删除 | 小改善 | 2 | II | done
27 | 济南版对应(编码规则) | 小改善 | 2 | II | dev-done | 预定 2011-4-24之前完成
28 | 1、压力数据采集有误，从修改0.07s采样数据开始。（已解决） | bug | 0.5 | I | done
29 | 2、监控界面的最小化按钮不工作。（是有时不工作） | bug | 0.1 | I | done
30 | 3、帮助“weld monitoring studio”并增加版本号。 | bug | 0.2 | I | done
31 | 4、英文版在中文系统安装报错。见“安装.jpg” | bug |  | I | done | 应该是偶发问题。请再测试。
32 | 5、同时打开多次同一文件。 | 小改善 | 1 | I | done
33 | 6、在曲线上，同时出现两个零 |  | 0 |  | Cancel
34 | 7、退出界面时很慢。 | bug | 3 | II | done
35 | 8、可两次打开“connect”,进度条变红色，并退出监控画面。 | bug | 0.5 | I | done
36 | 9、“onlineonstartup”功能未实现。 | bug | 1 | I | done
37 | 10、有时出现打不开监控界面情况。 | bug | 1 | II | done
38 | 重点：11、 必须修复：参数下载，下载固定参数。 | bug | 1 | I | done
39 | 12、监控界面：tonne 需要负值，不需要做去零处理。 | bug | 0.3 | I | done
40 | 13、压力计算公式，“计算公式.jpg” |  | 0 |  | cancel
41 | 14、对比plc参数，不同则显示“unknow”。 | 小改善 | 2 | I | done | 已更改。但我这里没有办法测试，不能确认是否已经OK了 预定 2011-4-24之前完成
42 | 15、在office版本增加Batche print(批量打印)。 | 较大改善 | 15 | IV | doing | 有限对应，只包括批量打印多个文件，不包括分类打印。单独预算
43 | 1、在关闭监控画面时，偶尔出现“close.jpg”故障。 | bug | 0.5 | I | done
44 | 2、pulse参数下载后，还是显示“unkown”,下载了三组参数，故障依旧. | bug | 0.5 | I | done
45 | 3、测试regular时，出现“regur.jpg” | bug | 0.3 | I | done
46 | reglar计算公式，有两个与Pluse不同。 a.flash speed=speed(low voltage stage) | 小改善 | 0.5 | II | done
47 | reglar计算公式，有两个与Pluse不同。 b.boost speed=speed(Boost last 3second) | 小改善 | 0.5 | II | done
| 1000 | Bug | 11.4 |  | 11400
| 21 |  | 11.4 |  | 11400
|  | 小改善 | 12.6 |  | 12600
|  | 大改善 | 23.3 |  | 23300
|  |  | 35.9 |  | 35900
|  | 较大改善 | 15 |  | 15000
|  |  | 15 |  | 15000